## XYZ
S. No. | Module | Requirement | Priority | Status | Requirement Given |  | Requirement |  |  |  | Comments
[5 empty] | Date | By | Discussed On | Total hrs Req. | Planned Delivery Date | Actual Delivery Date
1 | Examination | Question Paper Filling Report Version 2 |  | Deployed in Production | [5 empty] | 2024-04-10
2 |  | Back Examination Rule |  | Done |  |  |  |  | 2024-01-25 | 2024-01-25
3 |  | New Improved Center Mapping Process for Students |  | Deployed in Testing |  |  |  |  | 2024-01-23
4 |  | Summary N.R. as per attached sample |  | Done
5 |  | NEP-Question Paper Filling Report - Changes & New Requirement |  | Deployed in Production | [5 empty] | 2024-04-10
6 |  | StudentIdCardNo generation students data and query |  | New
7 | Pre-Examination | Exam Center Wise New Report |  | Done | 2024-01-11 |  | 2024-01-12 |  | 2024-01-19
8 |  | Fields need to be capture for main Exam form for program B. Ed should be 10th, 12th, UG, PG and Other qualification. Like course, Board, Rollno,year,obtain marks ,Max marks. all these details can also be printed on the exam form print and enrolment Form . |  | Done | 2024-01-11 |  | 2024-01-12 |  | 2024-01-24 | 2024-01-24
9 |  | Migration certificate also must be captured, if the student has his migration certificate, then he will enter his Migration number and issue date. |  | Done | 2024-01-11 |  | 2024-01-12 |  | 2024-01-24 | 2024-01-25
10 |  | Student can fill back paper in only two subjects |  | Already there | 2024-01-11 |  | 2024-01-12 |  | 2024-01-24 | 2024-01-24
|  | If the student intake year (2020)This means the student have given the first-year main exam in 2021 and the second-year main exam in 2022 ,Now in this exam Jan-2024 Consider as a Time Bard ,student can appear as an EX (Part Back ).-- |  | Done | 2024-01-11 |  | 2024-01-12 |  | 2024-01-24 | 2024-01-24
11 |  | Page is getting refresh while filling the student personal details. |  | Done | 2024-01-11 |  | 2024-01-12 |  | 2024-01-19 | 2024-01-24
12 |  | After selecting the previous board CCSU fields are not opening to capture previous education details. |  | Done | 2024-01-11 |  | 2024-01-12
13 |  | **We also require a roll list for the exam form we have done for the Examination session 2023-24 for Main/ Back/Ex and we require a separate Roll List report for Ex with header Ex and this need to be implement on NR as well. There are few things which needs to be fixed in the Roll List which is already shared with backend. Instead of 2024 there should be 2023 year on the mentioned places in the attached screenshot. Report name should be as per the report data. For e.g. RollList_LLB_Main_2023-24 |  | Done | 2024-01-11 |  | 2024-01-12 |  | 2024-01-19 | 2024-01-19
14 |  | Qualification Pages and changes for B.ED and B.ED Special |  | Done |  |  |  |  | 2024-01-25 | 2024-01-25
15 |  | Splitting PARTBACK and PAPERBACK for B.ED and B.ED special |  | Done |  |  |  |  | 2024-01-25 | 2024-01-25
16 |  | Examination Session changes |  | Done |  |  |  |  | 2024-02-03 | 2024-02-03
17 |  | Roll list Pdf Chanegs |  | Done |  |  |  |  | 2024-02-06 | 2024-02-07
18 |  | Classification Type and Classification Drop Downs for Exam set up configuration |  | On hold
19 |  | Subject Mapping changes in Subject Dashlet |  | Done
20 |  | Exam Center Master changes |  | Done
21 |  | Student allocation exam center |  | Done
22 |  | State, district , city dropdown in exam form |  | Deployed in production
23 |  | Centre wise roll list changes (subject code selection etc. ) |  | Deployed in production |  |  | 2024-01-11 |  |  | 2024-01-19
24 |  | Exam Form dashboard (Remove College name and intakeyear and in place of these two add a. Exam Category b. Exam Form Year c. Exam Form Month d. Pagination Need to add |  | Deployed in production |  |  | 2024-02-05
25 |  | Remove Aadhar card as Mandatory |  | Deployed in production |  |  | 2024-02-04 |  | 2024-02-05 | 2024-02-05
26 |  | Exam Form Query Dashboard is taking time to get load |  | Deployed in production |  |  | 2024-02-05
27 |  | Program outline is taking so much time |  | In Progress
28 |  | Enrollment form should not come for already enrolled student with ccsu |  | Deployed in production
29 |  | Mark Entry Pages Chages |  | Deployed in production
30 |  | Tabs loading issue |  | Deployed in production
31 |  | Roll List Pdf Chanegs |  | Deployed in production
32 |  | B.Ed & B.ED Special Question Paper Report |  | Deployed in production |  |  | 2024-03-13 |  | 2024-03-19 | 2024-03-19
33 |  | Those students who have deposited the prescribed fee for Minor Research Project along with the fifth semester examination form, should not be charged this fee in the sixth semester. Who have not paid this fee in the fifth semester will have to pay the same in the sixth semester. Fee for Minor Research Project must be charged |  | Deployed in production
34 |  | For 28561 students are there which filled 5th semester exam form and we have to collect Research Project fee from students. |  | Deployed in production |  |  | 2024-03-11 |  | 2024-03-11 | 2024-03-11
35 |  | Student is not allowed to fill the 2nd semester back with the 6th semester |  | Deployed in production |  |  | 2024-03-01 |  | 2024-03-05 | 2024-03-05
36 |  | Next semester for NON-NEP Semester UG program (update in student progression current semester and current year) |  | Deployed in production |  |  | 2024-03-14 |  | 2024-03-15 | 2024-03-15
37 |  | Next semester for NON-NEP Semester PG program (update in student progression current semester and current year) |  | Deployed in production |  |  | 2024-03-17 |  | 2024-03-17 | 2024-03-17
38 |  | Subject import for BACHELOR OF DESIGN |  |  |  |  | 2024-03-15 |  | 2024-03-15 | 2024-03-16
39 |  | Minor Research Project has to be shown in 6th Sem for all students: a. If any student has already paid this fee in 5th SEM, no need to charge again. b. For all other students, The paper would be mandatorily selected, but fee would be charged as applicable |  | Deployed in production |  |  | 2024-03-16 |  |  | 2024-03-20
40 |  | For all students who filled up 1st SEM Back Exam in Dec-23, paid up his exam fees but later their exams form were cancelled as per instruction received from CCU a. The fee paid in this would have to be adjusted against 6th Sem Exam Fee for Jun-24 b. The list would be provided by Shubham Kumar ASAP. |  | Deployed in production |  |  | 2024-03-16 |  |  | 2024-03-20
41 |  | If student has opted the minor subject in the 1st semester it should not get open in the next semester. Same for the 2nd year. (If opted in 3rd semester should not get open in 4th semester) |  | Deployed in production
42 |  | 1 minor course (if not opted in first semester) 4 credits that means if student has not opted the minor in the 1st semester, then student must opt in the 2 semester this check needs to be there. Same condition for the 2nd year. |  | Deployed in production
43 |  | Exam Form changes: For NEP: 1. Remove Theory,Lab credits and Paper id column. For Non NEP: 1. Remove paperid column from all Exam Form. |  | Deployed in production |  |  | 2024-03-01 |  | 2024-03-05 | 2024-03-05
44 |  | In vocational if student select any theory subject then automatically Practical subject should get auto select. |  | Deployed in production |  |  | 2024-03-04 |  | 2024-03-08 | 2024-03-08
45 |  | If student only selects Co-curricular classification then they should be able to pay 250/- only and If students fill back paper and selects co-curricular classification then fee will be normal which is 940/- |  | Deployed in production |  |  | 2024-03-04 |  | 2024-03-06 | 2024-03-06
46 |  | Update student progression for Non NEP programs |  | Deployed in production
47 |  | Mark entry (Internal/External) for Ex Students |  | Deployed in production | 2024-03-12 |  |  |  | 2024-03-22 | 2024-03-22
48 |  | B.ED URN Generation |  | Deployed in production |  |  | 2024-03-22 |  |  | 2024-03-27
49 |  | Back Paper Rule for non nep programs |  | Deployed in production
|  | Insert the subject mapping for the program M.SC ENVIROMENTAL SCIENCE |  | Deployed in production |  |  | 2024-03-23 |  |  | 2024-03-26
50 |  | B.ED/B.ED. Roll list and nominal roll list changes |  | Deployed in production |  |  | 2024-03-24
51 |  | open the exam form for RUSSIAN LANGUAGE AND FRENCH LANGUAGE odd semester exam for semester 1 |  | Deployed in production
52 |  | Front End feasiability for Program Mapping Rule |  | Deployed in production |  |  | 2024-04-05 |  |  | 2024-04-05
53 |  | Short Fee Adjustment |  | Deployed in production |  |  | 2024-04-05 |  |  | 2024-04-05
54 |  | Student object file for fee adjustment |  | Deployed in production |  |  | 2024-04-05 |  |  | 2024-04-05
55 |  | Student data file for migrate in the system |  | Deployed in production |  |  | 2024-04-07 |  |  | 2024-04-08
56 |  | Question Paper Filling Report for UG NEP programs |  | Deployed in production |  |  | 2024-04-04 |  |  | 2024-04-08
57 |  | Add Subject with reference number drop down against classifcationname in the drop down. (How many subject mapped to that classification type and name that needs to show in the drop down, if user selects any classification type and name. |  | Deployed in production
58 |  | Remove classification type and classification name from examcenterwise roll list |  | Deployed in production |  |  | 2024-04-13 |  |  | 2024-04-14
59 |  | Migrate the students in the system |  | Deployed in production |  |  | 2024-04-15 |  |  | 2024-04-16
60 |  | As required by CCSU, We need to disable following rule: 1. Student cannot fill Back and Main Exams together for SEM 2 & 6. |  |  |  |  | 2024-04-16 |  |  | 2024-04-19
61 |  | If other courses also mapped for any semester and intake year so we need to implement N/2 rule for the subject which is mapped for that particular intake year and semester for back paper. |  | Deployed in production
62 |  | Performance issue regarding exam form |  | Deployed in production
63 |  | Subject configuration dashlet loading issue |  | Deployed in production
64 |  | B.Ed & B.ED Special verification for college and university |  | Deployed in production
65 |  | New Student Exam Center Allocation |  | Deployed in Testing
66 |  | For B.VOC(AIRLINES, TOURISM AND HOSPITALITY MANAGEMENT) and B.VOC(MEDICAL LAB. & MOLECULAR DIAGNOSTICS TECHNOLOGY Program, Back Paper rule need to change |  | Deployed in production
67 |  | Add Drop Down of subjects in Exam Centerwise Roll list |  | Deployed in production
68 |  | If marksup break up is not there then user should not be able to land on Mark Entry Pages
69 |  | Naming convention for Question Paper need to discuss With Arvind
70 |  | For Colleges in affiliation_college table, status column was Pending for Some colleges which was added earlier. So made status column as Approved so, in mark entry pages subjects was not coming so this issue got resolved |  | Deployed in production
71 |  | Nominal summary Report Issue where some colleges nominal roll ist are not getting printed |  | Deployed in production | 2024-04-16 |  |  |  |  | 2024-04-16
72
73
74

## ABC
S. No. | Module | Requirement | Priority | Status | Requirement Given |  | Requirement |  |  |  | Comments
[5 empty] | Date | By | Discussed On | Total hrs Req. | Planned Delivery Date | Actual Delivery Date
1 | Pre-Examination | Feasibility to upload the internal marks by faculties with multiple sessional marks | Medium | New
2 | Fees | GUG requested us to simplify the fee payment process where the user will be configuring the Intake year wise Program wise fee for the program where they will be mentioning the fee bifurcation as well for the students to view it and to extract the reports. Need to Create the master for Fee Bifurcation where user will define the categories. | High | New
3 | Attendence | GUG requested us to introduce the subject wise and day wise attendance so that the everyday attendance shall be marked for the students. | Medium | New
4 | Employee | A new dashlet need to be introduced to create employee login | High | New
5 | Teaching Site | In Teaching site we need to add as new dashlet where the employees can add the Publications. | Urgent | Done
6 | Assignments | As per new functionality the students will be having the option to submit the assignment where they can submit the assignment to the facility they choose. Need to create new dashlet called submit assignment in student login Only for GUG students. | Medium | New
7 | RR and CRR Payment | As per GUG the active students count will be extracted based on CRR and RR payments done in Year. | High | New
8 | Fees | as requested by registrar audit and finance officer we need to extract the report where amount configured in our system versus amount paid by the students will be extracted based on intake year. We need to create two different reports where when is used for summary and another is for detailed fees paid by the students with headers: | Urgent | New
9 | Post Examination | GUG requested us to prepare the report of Marks Entry as report for all the students and all the semesters all together with marks update history where the student reappear attempts will occurs. | Urgent | Done
10 | Post Examination | Change Request Document for Student Marks Report | Urgent | Need to improve the logic | [6 empty] | College Dropdown valuse should be based on Program
11 | Fees | Finance data Ledger - Import and Export | Urgent | In-Progress |  |  | 2024-01-17
12 | Post Examination | Serial number and QR code Printing In DMC and FMC with Printing status | Urgent | Deployed in production | [5 empty] | 2024-02-24
13 | Conduct Exam | RLA reports shall be available in Fornt End | High | Done |  |  | 2024-01-17 |  |  | 2024-02-07
14 | RR Import | Marks Students active or Inactive after RR Import | Medium | New
15 | RR and CRR Payment | Select programs while doing RR, CRR, Exam fee payment | Medium | Done | [5 empty] | 2024-02-24
16 | Post Examination | RLA status in Gazette | High | Done
17 | Student Site | Student Login - Program Selection 1. E-Services 2. PMC 3. Fees 4. Rest all | Most Urgent | In-Progress |  |  | 2024-01-17
18 | Post Examination | changes in Gazette |  | Done | [5 empty] | 2024-02-07
19 | Post Examination | college downloads and stores all semester mark sheets for passed students in a designated templet |  | Deployed in production | [5 empty] | 2024-02-07
20 | BIRT Reports | Repost For DIGI locker - Shared over the email. Link: https://imtac-my.sharepoint.com/:x:/p/ankurm/EYWV8vP6OCVLlPQ2HGaC4nwBu1BveOtiNrMoe2gQR1StxQ?e=Hs54Pj | Urgent
21 | Post Examination | AB - Absent Shall be visible in Result Sheet as 'AB', Curently 0 is coming for student in result sheet and AB is visible in PMC, Examination Branch is facing the issues in Verification. | Urgent
22` | student fee recpit | student academic fee receipts for the current academic year. students have noticed that the academic year consistently displays as 2024-2025 for every session. | Urgent | Deployed In Production | [5 empty] | 2024-02-29
23 | Subject Grouping | Theory overall marks is not showing in PMC intake year 2022 sem 2 BACHELOR OF SCIENCE Same issue is facing for semester 4 intake 2021 Due to subject Grouping | Most Urgent
24 | Exam Form | Colleges are facing issue in exam form generation download as the count which is coming in exam form generation is not matching with Subject Booking count. And this need to solve ASAP because college need to submit the exam form in university after the verification and if the count will not same then they will be not able to submit the exam fee. | Urgent

## ENHANCEMENT
S.NO. | Description | CCSU | GU
1 | Bulk promote option for students in student progression | Need to implement
2 | Bulk option for updating college for students | Need to implement
3 | Program Outline, taking so much time to get load and some times not loading | Need to implement | Need to implement
4 | Delete Mark Entry |  | Need to implement
5 | Subject Grouping, its taking so muc time to get load, need to put referencenumber with courename |  | Need to implement
6 | After Processing/Reprocessing and Publishing and Republishing, user should not allow to change the marks breakup. |  | Need to implement
7 | Edit and delete payment history |  | Need to implement
8 | Subject Coniguration is taking time to get load